## Sheet1
ID	Description					Status
1	Identification of Revisions (Requirements)
2		Old options removed					Submitted
3		Old Options renamed					Submitted
4		New Options					Submitted
5		New Features					Submitted
6		Write up of the revisions into a release notes document					Submitted
7	Version number					3.4.1
8	Test SVN access to commit changes
9	Code Changes
10		Create new branch in git					Complete
11		Update with new version number
12			Version.sh					Submitted
13			config.c					Need Copyright
14			motion.1					Submitted
15
16		Create new branch in SVN
17		Create patch set for SVN					Submitted
18		Locally test commits for SVN					Complete
19		Commit changes to SVN
20	Code Testing
21		Valgrind memory check with RTSP					Pass
20	Build Testing
21		Debian (Wheezy, Jessie, Stretch)
22			Wheezy					Obsolete
23			Jessie					Complete
24			Stretch					Deferred
25		Ubuntu (14.04, 14.10, 15.04, 15.10)
26			14.04					Complete
27			14.10					Obsolete
28			15.04					Complete
29			15.10					Complete
30		PI (Wheezy Raspbian, Jessie?)
31			Raspbian Wheezy					Complete
32			Raspbian Jessie					Complete
33		OpenSuse(13.2)
34		CentOS 7					Complete
35		BSD					Needs Makefile changes
36	Packaging
37		DEBs
38			Debian
39
40				Jessie				Submitted(x64/i386)
41				Stretch
42			Ubuntu
43				14.04				Submitted(x64/i386)
44				14.10				Obsolete
45				15.04				Submitted(x64/i386)
46				15.10				Submitted(x64/i386)
47			PI
48				Raspbian Wheezy				Submitted(arm)
49				Raspbian Jessie				Submitted(arm)
50		RPMs
51			OpenSuse
52			CentOS
53		Tarball					Submitted
54		Update Sourceforge with new tarball
55	Wiki Changes
56		Determination of a plan for wiki changes
57			Identification of pages needing revision
58			http://www.lavrsen.dk/foswiki/bin/view/Motion/WebTopicList
59		Home page
60			Version number on left
61		Roadmap
62		Motion Guide
63			Configuration Options
64			One Large Document					Submitted
65		FAQ
66		Downloads
67		Support Requests
68			Identification of requests addressed to close
69			Close requests (To be completed after actual release)
70		Bug Reports
71			Identification of requests addressed to close
72			Close requests (To be completed after actual release)
73		Feature Requests
74			Identification of requests addressed to close
75			Close requests (To be completed after actual release)
76		Motion Patches
77			Identification of requests addressed to close
78			Close requests (To be completed after actual release)
79		Index
80	Issues
81		Copyright date from motion -h is incorrect					Pending
82		BSD Compile Issues					Pending
83			Makefile requires commenting out ifeq statements					Pending
84			Makefile sed commands fail					Pending
85			Message on gmake install vs make install (make worked)					Pending
86			No directory of /etc/motion					Pending
87			Many warnings on short vs int vs unsigned					Pending
88			Many warnings old style gnu format in conf.c, track.c					Pending
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108